## Task Plan
NeuroPathway (Social Innovation CIC) — Project Task Plan
Owners: You & Duane ¦ Alternating task ownership ¦ Timeline: ~4.5 months
Phase | Task | Owner | Start Date | End Date | Duration (days) | Status | Notes
1. Discovery & Research | Define mission, vision & theory of change for NeuroPathway | You | 2026-09-21 | 2026-09-27 | 6 | Not started
1. Discovery & Research | Research neurodivergent support landscape & unmet needs | Duane | 2026-09-28 | 2026-10-04 | 6 | Not started
1. Discovery & Research | Stakeholder interviews (families, schools, clinicians) | You | 2026-09-28 | 2026-10-11 | 13 | Not started
1. Discovery & Research | Competitor & landscape analysis | Duane | 2026-10-05 | 2026-10-11 | 6 | Not started
2. Legal & Governance | Choose CIC structure (guarantee vs shares) & advisor | You | 2026-10-12 | 2026-10-18 | 6 | Not started
2. Legal & Governance | Draft Articles of Association & CIC36 community interest statement | Duane | 2026-10-12 | 2026-10-25 | 13 | Not started
2. Legal & Governance | Recruit board members / non-exec directors | You | 2026-10-19 | 2026-11-01 | 13 | Not started
2. Legal & Governance | Register with Companies House & CIC Regulator | Duane | 2026-10-26 | 2026-11-01 | 6 | Not started
2. Legal & Governance | Open business bank account & set up bookkeeping | You | 2026-11-02 | 2026-11-08 | 6 | Not started
3. Program Design | Design NeuroPathway service model & curriculum | Duane | 2026-10-26 | 2026-11-15 | 20 | Not started
3. Program Design | Draft safeguarding, accessibility & data protection policies | You | 2026-11-09 | 2026-11-22 | 13 | Not started
3. Program Design | Build referral pathways with schools/NHS/charities | Duane | 2026-11-16 | 2026-11-29 | 13 | Not started
3. Program Design | Define pricing, subsidy & sliding-scale funding model | You | 2026-11-16 | 2026-11-22 | 6 | Not started
4. Funding & Resources | Map grant & social investment opportunities | Duane | 2026-11-23 | 2026-11-29 | 6 | Not started
4. Funding & Resources | Write and submit first grant applications | You | 2026-11-30 | 2026-12-13 | 13 | Not started
4. Funding & Resources | Set up donation platform & fundraising page | Duane | 2026-11-30 | 2026-12-06 | 6 | Not started
4. Funding & Resources | Recruit initial staff / sessional practitioners & volunteers | You | 2026-12-07 | 2026-12-20 | 13 | Not started
5. Brand & Marketing | Develop brand identity, name assets & website | Duane | 2026-12-07 | 2026-12-20 | 13 | Not started
5. Brand & Marketing | Build social media & community outreach plan | You | 2026-12-14 | 2026-12-20 | 6 | Not started
5. Brand & Marketing | Local press / community partner outreach | Duane | 2026-12-21 | 2026-12-27 | 6 | Not started
6. Pilot Launch | Recruit pilot cohort of participants/families | You | 2026-12-21 | 2027-01-03 | 13 | Not started
6. Pilot Launch | Run pilot NeuroPathway sessions | Duane | 2026-12-28 | 2027-01-17 | 20 | Not started
6. Pilot Launch | Collect participant feedback & outcome data | You | 2027-01-04 | 2027-01-17 | 13 | Not started
6. Pilot Launch | Evaluate pilot & refine service model | Duane | 2027-01-18 | 2027-01-24 | 6 | Not started
7. Full Launch | Plan and host public launch event | You | 2027-01-18 | 2027-01-24 | 6 | Not started
7. Full Launch | Publish year-one impact & funding roadmap | Duane | 2027-01-25 | 2027-01-31 | 6 | Not started
7. Full Launch | Set up ongoing monitoring & quarterly review cadence | You | 2027-01-25 | 2027-01-31 | 6 | Not started

## Summary
NeuroPathway CIC — Plan Summary
Project start | 2026-09-21
Project end (planned) | 2027-01-31
Total tasks | 27
Tasks — You | 14
Tasks — Duane | 13
Tasks done | 0